## Project Timeline
Kevin Hudson APISuperstor PROJECT TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-08-15 | Project Start August 15th | 25 | 1
2016-08-16 | Milestone 1 - 8/16 Setup wireframe Gather Resources turn in dsign documents | 10 | 1
2016-08-17 | Milestone 2 - 8/17 Format webpage in dramweaver (add images and wording) | -10 | 1
2016-08-18 | Milestone 3 - 8/18 Test current weblayout an functionality | 15 | 1
2016-08-19 | Milestone 4 - 8/19 fix errors encountered/research CSS techniques | -15 | 1
2016-08-20 | Milestone 5 - 8/20 Review website/ test functionality | 15 | 1
2016-08-21 | Milestone 6 - 8/21 turn in preview | -15 | 1
2016-08-22 | Milestone 7 -8/22 test website and research CSS | 15 | 1
2016-08-23 | Milestone 8 - 8/23 submit website to Slack for ese testing and feedback | -20 | 1
2016-08-24 | Milestone 9 - 8/24 review feedback given make adjustments | 20 | 1
2016-08-25 | Milestone 10 - 8/25 finalize website | -15 | 1
2016-08-26 | Project End - 8-26 turn in for a grade | 15 | 1